## Breakdown function (hidden)
User login | Main menu | Function | Parameters | Value
Admin | Resource Management | Add/Edit/Remove resource | ID
Name
Email
|  |  | State | PL
BKPL
Billable
BK
Trainee
Move out
| Title Management | Add/Remove title | Category
TOCK Code
Title Name
Title Color
GM Title Tracking
PTO DTO Tracking
| Performance Tracking | Show by month
Show by color of title
Device Tracking
User | Fill Bug Statistic | Today
Missing day
DTO PTO Info

## Estimation
| Estimated Days (2 HC) | Implemented Days (2 HC) | Remaining Days (2 HC)
P1 | 31.4375 | 22.875 | 8.5625
P2 | 5 | 3.6875 | 1.3125
P3 | 6 | 3.6875 | 2.3125
P4 | 6 | 3.6875 | 2.3125
Level | Main menu | Function | Priority | Estimated hours | Implemented hours | Developer | Status | 2015-10-14 | 2015-10-15 | 2016-01-08 | 2016-01-11 | 2016-01-12 | 2016-01-13 | 2016-01-14 | 2016-01-15 | 2016-01-18 | 2016-01-19 | 2016-01-20 | 2016-01-21 | 2016-01-22 | 2016-01-25 | 2016-01-26 | 2016-01-27 | 2016-01-28 | 2016-01-29 | 2016-02-01 | 2016-02-02 | 2016-02-03 | 2016-02-04 | 2016-02-05 | 2016-02-15 | 2016-02-16 | 2016-02-17 | 2016-02-18 | 2016-02-19 | 2016-02-22 | 2016-02-23 | 2016-02-24 | 2016-02-25 | 2016-02-26 | 2016-02-29 | 2016-03-01 | 2016-03-02 | 2016-03-03
Home Page | Design UI/MasterPage |  | P1 | 24 | 16 | Thai Pham + Tan Vo | Completed | 2016-01-11: 4; 2016-01-14: 2; 2016-01-26: 1; 2016-02-01: 1
| Login/Logout function |  | P1 | 16 | 17 | Thai Pham | Completed | 2015-10-14: 2; 2015-10-15: 3; 2016-01-08: 8; 2016-01-11: 4
Admin Page | Resource Management | Add/Edit/Remove resource | P1 | 16 | 13 | Tan Vo | Completed | 2016-01-25: 8; 2016-01-26: 5
|  | Resource Allocation (Manual) | P1 | 150 | 165 | Thai Pham + Tan Vo | Completed | [5 empty] | 8 | 8 | 3 | 8 | 8 | 8 | 8 |  | 8 | 2 | 8 | 8 | 8 | 2 | 6.5 | 11 | 7 | 3.5 | 3.5 | 2 | 7 | 7.5 | 7.5 | 1 | 7.5 | 2 |  |  |  |  | 6 | 6
|  | Resource Allocation (Automated) | P4 | 24 |  |  | Not start yet
| Title Management | Add/Edit/Remove title | P1 | 55 | 51 | Tan Vo | Completed | 2016-01-13: 6; 2016-01-14: 6; 2016-01-15: 8; 2016-01-18: 8; 2016-01-19: 7; 2016-01-20: 8; 2016-01-21: 8
|  | Add/Edit/Remove title category | P1 | 16 | 8 | Tan Vo | Completed | 2016-01-22: 8
|  | GM Title Tracking | P3 | 24 | 0 |  | Not start yet
| PTO/DTO Tracking | Add upcoming PTO/DTO | P2 | 24 | 0 |  | Not start yet
|  | Show by week | P2 | 16 | 0 |  | Not start yet
|  | Show by month | P2 | 8 | 0 |  | Not start yet
|  | Show by year | P2 | 8 | 0 |  | Not start yet
| Performance Tracking | Fill Bug Statistic | P1 | 30 | 17 | Tan Vo | Completed | 2016-01-26: 2; 2016-01-27: 4; 2016-02-01: 6; 2016-02-03: 5
|  | Show by month | P1 | 50 | 21.5 | Thai Pham | In progress | 2016-02-25: 7; 2016-02-26: 6; 2016-02-29: 4.25; 2016-03-01: 3.25; 2016-03-02: 1
|  | Show number of working day by title color | P1 | 24 | 0 |  | Not start yet
|  | Show number of bugs by title color | P1 | 24 | 0 |  | Not start yet
|  | Show all color or specific color | P1 | 24 | 0 |  | Not start yet
| Billing list |  | P1 | 16 | 21 | Tan Vo | Completed | 2016-02-16: 8; 2016-02-17: 8; 2016-02-18: 5
| Device/Chip Tracking | Add/Edit/Remove device | P4 | 16 | 0 |  | Not start yet
|  | Add/Edit/Remove chip | P4 | 16 | 0 |  | Not start yet
| FB Tracking | Send FB | P3 | 8 | 0 |  | Not start yet
|  | Collect FB | P3 | 16 | 0 |  | Not start yet
| Data Analyzing | By Tester | P2 | 24 | 59 | Tan Vo | In progress | 2016-02-19: 8; 2016-02-22: 8; 2016-02-23: 1; 2016-02-25: 5; 2016-02-26: 7; 2016-02-29: 7; 2016-03-01: 7; 2016-03-02: 8; 2016-03-03: 8
|  | By Title | P4 | 24 | 0 |  | Not start yet
| Non-work Hours Tracking | Create | P3 | 8 | 0 |  | Not start yet
|  | Collect | P3 | 16 | 0 |  | Not start yet
User Page | DTO PTO Info | View upcoming PTO/DTO | P3 | 8 | 0 |  | Not start yet
| Device/Chip Tracking | View device | P4 | 8 | 0 |  | Not start yet
|  | Add/Edit/Remove chip | P4 | 8 | 0 |  | Not start yet
| FB Tracking | Send FB | P3 | 8 | 0 |  | Not start yet
| Non-work Hours Tracking | Create | P3 | 8 | 0 |  | Not start yet
Other | Setup Enviroment |  | P1 | 4 | 0 | Thai Pham + Tan Vo | Completed
| Design DB and DB Relationship |  | P1 | 16 | 16.5 | Thai Pham + Tan Vo | In progress | 2015-10-14: 1; 2015-10-15: 1; 2016-01-13: 2; 2016-01-19: 1; 2016-02-01: 1; 2016-02-24: 7.5; 2016-02-26: 1; 2016-02-29: 1; 2016-03-01: 1
| Setup and get famliar Github |  | P1 | 4 | 4 | Thai Pham + Tan Vo | Completed | 2016-01-12: 4
| Resolve the issue related to: - Github |  | P1 | 5 | 5 | Thai Pham | Completed | 2016-01-15: 5
| Fix bugs: - Resource Allocation (Manual) - Bug Statistics - Fix issues related to the Js files from Microsoft on Ớ's PC |  | P1 | 5 | 5 | Thai Pham + Tan Vo | Completed | 2016-02-16: 5; 2016-02-18: 3; 2016-02-22: 6.5; 2016-02-23: 7; 2016-02-24: 6; 2016-02-25: 3; 2016-02-29: 1
| Input data to DB |  | P1 | 16 | 3 | Thai Pham | In progress | 2016-02-15: 3
| Publish LFCRM |  | P1 | 8 | 3 | Thai Pham | Completed | 2016-02-05: 3
Total |  |  |  | 775 | 422 |  | In progress | 3 | 4 | 8 | 8 | 4 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 8 | 16 | 10 | 12 | 8 | 8 | 10 | 6.5 | 16 | 7 | 6.5 | 6.5 | 15 | 15 | 15.5 | 15.5 | 15.5 | 15.5 | 15.5 | 15 | 14 | 13.25 | 11.25 | 15 | 14

## DB Relationship
Table | Field
tbl_User | UserID | auto increment
EmployeeID
UserRoleID
FullName
Email
Password
Phone Number
Active
tbl_UserRole | UserRoleID | auto increment
RoleName
tbl_ProjectRole | ProjectRoleID | auto increment
| ProjectRoleName | PL | C | T | BK
Abbreviation
tbl_Title | TitleID | nvarchar(50)
3LD
TitleCategoryID
TOCKCode
TitleName
ColorCode
tbl_TitleCategory | TitleCategoryID
Category
ColorCode
tbl_ResourceAllocation | ID
Date
UserID
ProjectRoleID
TitleID
WorkingHoursID
tbl_TitleAllocation | ID
Date
TitleID
ExpectedResourceQuantity
ActualResourceQuantity
TrainResourceQuantity
tbl_WorkingHours | WorkingHoursID | auto increment
Value
BugID
tbl_BugTracking | Date
UserID
TitleID
NumberOfBugs
tbl_StatePerDay | StatePerDayID | Core | Billable | Shadow
StatePerDay
tbl_TimeAwayCategory | TimeAwayID
TimeAwayName
tbl_TimeAwayTracking | EmployeeID
TimeAwayID
Date
Hours
tbl_FeedBack | FeedbackID | auto increment
Date
UserSendID
UserReceiveID
TitleID
Message
Point
tbl_BugHunter | BugHunterID | auto increment
Month
UserID
Rate

## Common Css
Type | Value
Table | table table-striped table-bordered table-responsive table-condensed table-hover
Textbox | form-control
Dropdownlist | form-control
button | btn btn-success
error label | label label-danger

## Bug
Page | Summary
Title Manager | - Unable to search Title after Add/Edit/Delete Title | Done
BugStatistic | - Bug number should be saved after unchecking checkbox | Done

## Sheet1
OT
Profile