## Breakdown function (hidden)
User login | Main menu | Function | Parameters | Value
Admin | Resource Management | Add/Edit/Remove resource | ID
Name
Email
|  |  | State | PL
BKPL
Billable
BK
Trainee
Move out
| Title Management | Add/Remove title | Category
TOCK Code
Title Name
Title Color
GM Title Tracking
PTO DTO Tracking
| Performance Tracking | Show by month
Show by color of title
Device Tracking
User | Fill Bug Statistic | Today
Missing day
DTO PTO Info

## Estimation
Level | Main menu | Function | Priority | Estimated hours | Implemented hours | Developer | Status | 2015-10-14 | 2015-10-15 | 2016-01-08 | 2016-01-11 | 2016-01-12 | 2016-01-13
Home Page | Design UI/MasterPage |  | P1 | 24 | 12 | Thai Pham | In progress | 2016-01-11: 4
| Login/Logout function |  | P1 | 16 | 17 | Thai Pham | Completed | 2 | 3 | 8 | 4
Admin Page | Resource Management | Add/Edit/Remove resource | P1 | 16 |  |  | Not start yet
|  | Resource Allocation (Manual) | P1 | 24 |  | Thai Pham | Not start yet
|  | Resource Allocation (Automated) | P4 | 24 |  |  | Not start yet
| Title Management | Add/Edit/Remove title | P1 | 16 |  | Tan Vo | Not start yet
|  | Add/Edit/Remove title category | P1 | 16 |  | Tan Vo | Not start yet
|  | GM Title Tracking | P3 | 24 |  |  | Not start yet
| PTO/DTO Tracking | Add upcoming PTO/DTO | P2 | 24 |  |  | Not start yet
|  | Show by week | P2 | 16 |  |  | Not start yet
|  | Show by month | P2 | 8 |  |  | Not start yet
|  | Show by year | P2 | 8 |  |  | Not start yet
| Performance Tracking | Fill Bug Statistic | P1 | 24 |  |  | Not start yet
|  | Show by month | P1 | 24 |  |  | Not start yet
|  | Show number of working day by title color | P1 | 24 |  |  | Not start yet
|  | Show number of bugs by title color | P1 | 24 |  |  | Not start yet
|  | Show all color or specific color | P1 | 24 |  |  | Not start yet
| Device/Chip Tracking | Add/Edit/Remove device | P4 | 16 |  |  | Not start yet
|  | Add/Edit/Remove chip | P4 | 16 |  |  | Not start yet
| FB Tracking | Send FB | P3 | 8 |  |  | Not start yet
|  | Collect FB | P3 | 16 |  |  | Not start yet
| Data Analyzing | By Tester | P2 | 24 |  |  | Not start yet
|  | By Title | P4 | 24 |  |  | Not start yet
| Non-work Hours Tracking | Create | P3 | 8 |  |  | Not start yet
|  | Collect | P3 | 16 |  |  | Not start yet
User Page | DTO PTO Info | View upcoming PTO/DTO | P3 | 8 |  |  | Not start yet
| Device/Chip Tracking | View device | P4 | 8 |  |  | Not start yet
|  | Add/Edit/Remove chip | P4 | 8 |  |  | Not start yet
| FB Tracking | Send FB | P3 | 8 |  |  | Not start yet
| Non-work Hours Tracking | Create | P3 | 8 |  |  | Not start yet
Other | Setup Enviroment |  | P1 | 4 | 4 | Thai Pham | Completed
| Design DB and DB Relationship |  | P1 | 16 | 14 | Thai Pham | In progress | bar: 2015-10-14 to 2015-10-15
| Setup and get famliar Github |  | P1 | 4 | 4 | Thai Pham + Tan Vo | Completed | 2016-01-12: 4
| Input data to DB |  | P1 | 16 |  |  | Not start yet
| Publish LFCRM |  | P1 | 8 |  |  | Not start yet
Total |  |  |  | 552 | 51 |  | In progress | 3 | 4 | 8 | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
OT
Profile

## DB Relationship
Table | Field
tbl_User | EmployeeID
UserRoleID
FullName
Email
Password
Phone Number
Active
tbl_UserRole | UserRoleID
RoleName
tbl_ProjectRole | ProjectRoleID
| ProjectRoleName | PL | C | T | BK
tbl_Title | TitleID
TitleCategoryID
TOCKCode
TitleName
TitleColor
tbl_TitleCategory | TitleCategoryID
Category
Color
tbl_ResourceAllocation | Date
EmployeeID
ProjectRoleID
TitleID
ExpectedResourceQuantity
ActualResourceQuantity
tbl_BugTracking | Date
EmployeeID
Title ID
NumberOfBugs
tbl_StatePerDay | StatePerDayID | Core | Billable | Shadow
StatePerDay
tbl_TimeAwayCategory | TimeAwayID
TimeAwayName
tbl_TimeAwayTracking | EmployeeID
TimeAwayID
Date
Hours